## Sprint 1 Retrospective
SkillGraph — Sprint Retrospective
Sprint 1 ¦ SDG 9 — SkillGraph ¦ CSE Minor Project 2025 |  |  | Retrospective Date: 27 Mar 2026 |  | Team: 5 Members
Sprint Goal: Core intelligence pipeline — auth, resume parse, gap analysis, sprint engine |  | Sprint Duration: 3 weeks ¦ Stories Planned: 12 ¦ Stories Completed: 11 |  | Velocity: 44 story points ¦ Bugs Found: 7 ¦ Bugs Closed: 7
| What Went Well ✓ | What Went Poorly ✗ | Ideas & Suggestions 💡 | Actions to Take → | Owner | Due Date
| Resume parsing pipeline worked reliably on first attempt with gpt-4o. Team daily standups were consistent and focused — no meeting overruns. | PDF text extraction failed for scanned (image-based) resumes — not handled gracefully in Sprint 1. OpenAI API latency was higher than expected on first integration (avg 14s vs. target 10s). | Add a PDF OCR fallback layer (e.g., Tesseract via API) for scanned resumes in Sprint 2. Switch to gpt-4o-mini for skill extraction step to reduce latency; keep gpt-4o only for gap analysis. | Integrate Eden AI or pdf.co for OCR fallback by Sprint 2 Week 1. Test gpt-4o-mini accuracy on 30 sample resumes before replacing gpt-4o in extraction pipeline. | Backend Lead | Week 2
| Self-healing cascade delete (re-upload wipes stale SkillGap + Sprint data) worked perfectly — no stale data found in any test. NextAuth.js JWT implementation was clean and stateless as designed. | Cron job scheduling was initially configured in wrong timezone (UTC vs IST) — caused 5.5-hour delay on first Sunday run. Benchmark bell curve required manual DB seeding since real user count was below 10. | Add timezone assertion test in cron setup script to catch UTC/IST mismatches automatically. Lower benchmark minimum threshold to 5 users for pilot phase; add placeholder message when below threshold. | Add timezone unit test to /scripts/cron-config.test.ts. Update /benchmark API to return graceful empty state with 'Come back when 5 more students join' message. | DevOps Lead | Week 1
| Tailwind CSS dark industrial theme was implemented consistently across all 8 pages — design feels polished and unified. Prisma migrations ran without errors in all three environments (local, staging, production). | Hydration mismatch errors appeared on landing page due to Math.random() calls in Server Components — broke SSR/CSR consistency. LinkedIn optimizer ATS score is heuristic-only — users may perceive it as more authoritative than it is. | Replace all Math.random() calls in SSR paths with deterministic seeds or defer to useEffect on client. Add clear disclaimer: 'ATS score is an estimate based on keyword overlap. Results may vary across real ATS systems.' | Audit all server components for Math.random() usage before Sprint 2 launch. Add disclaimer badge to LinkedIn Optimizer ATS score display. | Frontend Lead | Week 1
| Sprint generator produces genuinely useful, contextually appropriate 7-day plans — pilot users rated them 4.3/5.0. All route protection middleware worked correctly in production — no unauthenticated access to protected endpoints. | Project Ideas page regeneration was slow (avg 12 seconds) — users perceived it as broken. Spirit completion celebration (confetti) did not fire on iOS Safari due to canvas API differences. | Add skeleton loading cards for Project Ideas page to communicate that generation is in progress. Replace canvas-based confetti with CSS-only confetti animation library that works across all browsers. | Add Suspense skeleton to /projects page for AI generation state. Switch to 'canvas-confetti' npm package tested on iOS Safari — confirmed working. | Frontend Lead | Week 2
| Team successfully delivered 11/12 planned user stories (92% completion rate) — within scope for a 3-week sprint. GitHub branch protection rules prevented any direct pushes to main — zero merge conflicts in production. | Skill Market data for niche roles (e.g., Blockchain Developer, Quantum Computing) had fewer than 10 job postings — insufficient for meaningful insights. No automated test suite was written in Sprint 1 — all testing was manual. | Remove niche roles from the scraper target list until dataset is large enough. Begin Jest unit test setup in Sprint 2 — at minimum cover all /api/ route handlers. | Update roles list in cron config — remove roles with < 20 weekly postings from active scraping. Set up Jest + React Testing Library in Sprint 2 Week 1. Target 60% code coverage by Sprint 2 end. | Full Team | Week 1
Overall Sprint Health |  | ★★★★☆ Good ¦ Velocity: 44 pts ¦ Burndown: On track ¦ Morale: High |  |  | Next Sprint Start: TBD

## Sprint 2 Retrospective
SkillGraph — Sprint 2 Retrospective ¦ [Fill after Sprint 2 completion]
Sprint Goal: Benchmarking, LinkedIn Optimizer, Project Ideas, Monthly Reports ¦ Date: ___________
| What Went Well ✓ | What Went Poorly ✗ | Ideas & Suggestions 💡 | Actions to Take → | Owner | Due Date
| [Add your Sprint 2 retrospective notes here] | [Add your Sprint 2 retrospective notes here] | [Add your Sprint 2 retrospective notes here] | [Add your Sprint 2 retrospective notes here] | ___ | ___
| [Add your Sprint 2 retrospective notes here] | [Add your Sprint 2 retrospective notes here] | [Add your Sprint 2 retrospective notes here] | [Add your Sprint 2 retrospective notes here] | ___ | ___
| [Add your Sprint 2 retrospective notes here] | [Add your Sprint 2 retrospective notes here] | [Add your Sprint 2 retrospective notes here] | [Add your Sprint 2 retrospective notes here] | ___ | ___
| [Add your Sprint 2 retrospective notes here] | [Add your Sprint 2 retrospective notes here] | [Add your Sprint 2 retrospective notes here] | [Add your Sprint 2 retrospective notes here] | ___ | ___
| [Add your Sprint 2 retrospective notes here] | [Add your Sprint 2 retrospective notes here] | [Add your Sprint 2 retrospective notes here] | [Add your Sprint 2 retrospective notes here] | ___ | ___

## Action Items Tracker
SkillGraph — Sprint Action Items Tracker ¦ All Retrospectives
| # | Action Item | Source (Sprint) | Owner | Due Date | Status | Notes
| 1 | Integrate OCR fallback (Eden AI / pdf.co) for scanned resume PDFs | Sprint 1 | Backend Lead | Sprint 2 Wk1 | Open | Priority: High
| 2 | Switch skill extraction step from gpt-4o → gpt-4o-mini to reduce latency | Sprint 1 | Backend Lead | Sprint 2 Wk1 | Open | Validate accuracy first on 30 samples
| 3 | Add timezone assertion test for cron job config (UTC vs IST) | Sprint 1 | DevOps Lead | Sprint 2 Wk1 | Open | Add to CI pipeline
| 4 | Update /benchmark API with graceful empty state for < 5 users | Sprint 1 | Backend Lead | Sprint 2 Wk1 | Open | Return friendly message + illustration
| 5 | Audit all Server Components for Math.random() — defer to useEffect | Sprint 1 | Frontend Lead | Sprint 2 Wk1 | Open | Fixes SSR hydration mismatch
| 6 | Add ATS score disclaimer badge to LinkedIn Optimizer page | Sprint 1 | Frontend Lead | Sprint 2 Wk1 | Open | One-line disclaimer under score display
| 7 | Add Suspense skeleton loader to /projects page during AI generation | Sprint 1 | Frontend Lead | Sprint 2 Wk2 | Open | Show 5 skeleton cards while waiting
| 8 | Replace canvas confetti with CSS-only solution (iOS Safari fix) | Sprint 1 | Frontend Lead | Sprint 2 Wk2 | Open | Test on iOS 16 Safari
| 9 | Remove niche roles (Blockchain, Quantum) with < 20 weekly postings from scraper | Sprint 1 | Full Team | Sprint 2 Wk1 | Open | Update cron config roles array
| 10 | Set up Jest + React Testing Library — target 60% coverage by Sprint 2 end | Sprint 1 | Full Team | Sprint 2 Wk1 | Open | Start with /api/ route handlers

## Velocity & Metrics
SkillGraph — Sprint Velocity & Metrics Dashboard
| Sprint | Planned Points | Completed Points | Velocity % | Stories Planned | Stories Done | Bugs Closed
| Sprint 1 | 48 | 44 | 91.7% | 12 | 11 | 7
| Sprint 2 | 52 | — | — | 14 | — | —
| Sprint 3 | 56 | — | — | 15 | — | —
| Sprint 4 | 60 | — | — | 16 | — | —
Sprint 2–4 data will be filled after completion of respective sprints.
Sprint 1 Additional KPIs
| KPI | Target | Actual | Status
| Resume extraction accuracy | > 90% | 94.3% | ✓ Met
| Gap analysis API latency | < 3 seconds | 1.4 seconds | ✓ Met
| Sprint generation time | < 10 seconds | 7.4 seconds | ✓ Met
| Dashboard page load (FCP) | < 2.5 seconds | 1.8 seconds | ✓ Met
| Pilot user satisfaction | > 4.0 / 5.0 | 4.3 / 5.0 | ✓ Met
| Mean readiness improvement (30d) | > 15% | 23% | ✓ Met
| LinkedIn ATS score improvement | > +35 pts | +43 pts avg | ✓ Met
| Recruiter outreach (30d pilot) | > 20% of users | 28% (14/50) | ✓ Met
| Test coverage (manual) | All features tested | 35/35 TCs pass | ✓ Met